## HTML
Sr. No. | Review Comments | Status
1 | Change <meta charset="UTF-8"> to <meta charset="utf-8"> as per the standard mentioned here: https://google.github.io/styleguide/htmlcssguide.html#Encoding | Completed
2 | Move the script tag in head tag to the end of body tag. | Completed
3 | Add dummy favicon for now | Completed
4 | Rename html file to "index.html" | Completed
5 | Remove trailing white spaces within the code | Completed
6 | Content width is fixed, so make the changes accordingly. | Completed
7 | "Our Drones" should be "Our drones". | Completed
8 | Use hyphens in id attributes' values. No camelcasing required. For e.g.: aboutus => about-us Same applies for classnames | Completed
9 | For mobile hamburger menu, use button element instead of anchor tag | Completed
10 | In nav bar, use "ul li a" only. No need to use button separately. Instead you can use pseudo classes in css to achieve the styling. | Completed
11 | For logo image change the link. Instead of "./images/…" use "images/…." | Completed
1 | Date: 06/05/2018
2 | <li><a class="contact-btn" href="#contact-us">Contact</a></li>, here no need add separate class, you can use "links" and in active state you can manage the css | Completed
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37

## CSS
Sr. No. | Review Comments | Status | Comments
Date:
1 | Arrange the properties alphabetically | Completed
2 | Hamburger menu icon is not aligned in middle to the logo | Completed
3 | Reset all the browser defaults. Ref.: https://meyerweb.com/eric/tools/css/reset/reset.css | Completed
Date: 06/04/2018
1 | In ".container" class, is font-size required? Check and confirm. | Completed | Removed the font-size property
2 | Use shorthand property for background and other properties too, throughout the code | Completed
3 | "margin: auto" is used many times, is that really required? Check and confirm. | Completed | Removed "margin: auto" where it is not required.
4 | ".navbar .menu-icon" and ".navbar .close-icon" contains same properties which can be merged into ".navbar" only | Completed | merged
5 | Use hex values only for color, do not use color names, viz.: darkblue, also convert rgba code into hex code too. | In Progress | suggestions required
6 | Avoid use of -ve values, unless it is really required. | Completed | removed -ve value for margin.
Date: 06/05/2018
1 | reset css is not resetting all the browser defaults | Completed
2 | ".sub-container{", there should be a space before opening curly braces. Please check and update throughout. Ref.: https://google.github.io/styleguide/htmlcssguide.html#Declaration_Block_Separation | Completed
3 | For margin: auto, try using margin: 0 auto, if you want only the content in center from left and right | Completed
4 | add a new line after closing curly braces throughout the code | Completed
5 | Avoid targetting elements directly, instead target classes to add properties | Completed
6 | All hex values should be in lowercase, check throughout the code | Completed
7 | Add outline: none to all buttons, except required for the ones where it is required | Completed
8 | Convert colornames to their respective hex codes. For e.g. "gray" | Completed
9 | Individual selectors should be on new line, if using comma separated selectors | Completed
10
11
12
13
14
15

## JS
Sr. No. | Review Comments | Status
1 | Variables should be declared at the top in one function | Completed
2 | use strict | Completed
3 | "var x" doesn't define / specify anything as to what that variable is declared or used for. Use meaningful and concise variable names | Completed
4 | Add js docs wherever possible | Completed
5 | Use prototype based approach to write various functions | Completed
6 | Avoid using "innerHTML", as it may lead to security issues. | Completed
7 | Use event listeners in js itself instead of adding "onclick" or "onload", etc. in your template file | Completed
8 | Instead of using "x.className +=" using "x.classList.add()" or "x.classList.remove()" method | Completed
9 | Template manipulation should be handled in html/css. only dynamic handling of different should be manipulated through js | Completed
10 | Add an init function to declare variables and to call all various functions through the same | Completed
11 | Alongwith above comment add onload event to load init function as soon as the window objects loads | Completed
1 | Date: 06/05/2018
2 | Try to implement smooth scroll functionality | Completed
3 | Add custom email validation and use input type text instead of email in html template | In Progress
4
5
6
7
8
9
10
11